## Slide 1: Sawadeeka and Mauri from Kiribati
Training on coding causes of death and generating cause of death statistics within a national statistical system

## Slide 2: Brief background
The main issue that Kiribati faces is poor mortality coding and statistic, resulting in Kiribati having the highest birth rate in the Pacific.
The Government of Kiribati has recognised the need for more accurate, timely and relevant health information to inform planning, policy development and the monitoring of health sector performance.

## Slide 3: Activities that have taken place
1. A revised MCCD (DC) according to WHO approved international standard has been developed and is ready to be rolled out.
2. Training and capacity building of Kiribati doctors on accurate certification of Cause of Death was successfully implemented.
3. Kiribati health databases were updated and all the health indicators that could be derived from the existing routine data from the Kiribati health databases (KHIS & MS1) were formulated. Annual Health Bulletin 2015 has been released.

## Slide 4: Pending activities
4. Training & capacity building of Kiribati coders on Morbidity & Mortality coding in ICD-10 (pending) - time of implementation towards the latter part of the year (October or November 2016)
5. Training & capacity building of Kiribati coders on Medical Terminology (pending) - time of implementation towards the latter part of the year (October or November 2016)

## Slide 5: Stakeholders involved in implementation
Ministry of Health and Medical Services (MHMS)
WHO
Others like NGO’s and SPC

## Slide 6: Outcomes
WHO approved MCCD for the Ministry of Health,
A set of well trained doctors on certification of COD
Long term outcome - improved mortality data (pending)
Systems (MS1 and KHIS) will be upgraded to add more tabs for death coding, at the moment only one cause of death for both the systems.

## Slide 7: Challenges
Short number of staff
Getting a suitable consultant to carry out the tasks
Revision of the two available systems MS1 and KHIS to capture the correct format of MCCD – is underway
those currently involved in the mortality process - collection, analysis and use of the data – have a strong belief in the importance of the data. However, there is no one person or body at this point who has overall responsibility for mortality processes. This key body is needed in order to drive any medium- and long-term strategy for further development.

## Slide 8: Lessons learned
An HIU officer was trained in analysing the health databases and calculating relevant health indicators

## Slide 9: Recommendations
Secure services of a suitable consultant to carry out the remaining/pending tasks by requesting the WHO or any other NGO for assistance

## Slide 10
Kap khun kaa and Kam rabwa!